## Project Timeline
Project Timeline (Pacfic Time)
Project Milestones
Date | Milestone | Time Length | Position | Baseline | Project Timeline Tip
2016-05-07 | Project Start |  | 20 | 0 | Use the Position field in the Project Milestones table to place the milestone labels where you want! Use positive numbers to position them above the timeline and negative numbers to position them below.
2016-05-08 | Read Materials (React & GraphQL) | 2~3 hours | 10 | 0
2016-05-09 | Project Decisions -- frontend; Read Materials (React & TODOMVC) | 2~3 hours | -10 | 0
2016-05-10 | Modified Home Page Interface | 1~2 hours | 25 | 0
2016-05-11 | Search Dow Jones Stocks Data; Generate JSON files; Design and Develop List Page | 3~4 hours | -15 | 0
2016-05-12 | Develop List Page; Test and Debug | 2~3 hours | 15 | 0
2016-05-13 | Read Materials (d3); Design and Develop Home Page (User Input Area) | 2~3 hours | -15 | 0
2016-05-14 | Design and Develop Home Page (Stock Screener Area); Test and Debug | 2~3 hours | 15 | 0
2016-05-15 | Read Materials (SQLite, Dropwizard, etc.); Generate sqlite database | 1~2 hours | -20 | 0
0
0
0
0